## Summary
Schedule | Site | Total (Ex GST)
A1 | SITE1 - Cabbagetree Creek | 0
A2 | SITE 2 - Unnamed Creek CH 51640 | 0
A3 | SITE 3 - Stabilisation Ch 59250 - 59400 | 0
A4 | SITE 4 - Stabilisation Ch 61550 - 61800 | 0
A5 | SITE 5 - Christmas Creek | 0
A6 | SITE 6 - Ross Creek | 0
A7 | SITE 7 - Stabilisation Ch 73700 - 74000 | 0
A8 | SITE 8 - Sunnyside Slopes | 0
A9 | SITE 9 - Unnamed Creek Ch 76800 | 0
A10 | SITE 10 - Cracow Creek | 0
A11 | SITE 11 - Downfall Creek | 0
| Total | 0

## A1 - Schedule
SITE 1 - Cabbagetree Creek
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 441.8 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 223.2 | m2 |  | 0
Protective Treatments
2631 | Hand placed concrete paving, [175] mm thick, (including cutoff walls) as per project drawings and std drg CMDG-R-094 | 280 | m2 |  | 0
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 225.4 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional Item, If Ordered) | 35.2 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 2103 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 105 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 349 | m2 |  | 0
3108P | Excavation and disposal of Unsuitable Material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 32 | m3 |  | 0
3109P | Excavation and disposal of Unsuitable Material with individual excavation >= 10 m^3 (Provisional Quantity, as directed) | 32 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 984 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 24 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 34 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 16 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 2120 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 63.6 | m3 |  | 0
Unbound Pavements
4102 | Subtype 2.3, Unbound pavement, [floodway] | 56 | m3 |  | 0
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 290.6 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 382 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 4 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 382 | m2 |  | 0
Road Deliniation
6301 | Spotting for longitudinal lines | 40 | m |  | 0
6302 | Pavement marking (all types) | 40 | m |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 8 | each |  | 0
6112 | Road edge guide posts (flexible tubular) | 10 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
|  |  |  | TOTAL | 0

## A2 - Schedule
SITE 2 - Unnamed Creek 1 Floodway CH 51640 - 51775m
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 289 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 34 | m2 |  | 0
Protective Treatments
2631 | Hand placed concrete paving, [175] mm thick, (including cutoff walls) as per project drawings and std drg CMDG-R-094 | 208 | m2 |  | 0
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 102.8 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional, If Ordered) | 5.2 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 2171 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 150 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 679 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 35 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 35 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 1580 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 24 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 35 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 16 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 2302.6 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 69.1 | m3 |  | 0
Unbound Pavements
4102 | Subtype 2.3, Unbound pavement, [floodway] | 41.6 | m3 |  | 0
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 316.4 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 219 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 2.3 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 219 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 17 | each |  | 0
6112 | Road edge guide posts (flexible tubular) | 8 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
Road Deliniation
6301 | Spotting only for longitudinal lines | 32 | m |  | 0
6302 | Pavement marking (all types) | 32 | m |  | 0
|  |  |  | TOTAL | 0

## A3 - Schedule
SITE 3 - Stabilisation Ch 59250 - 59400
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Supply and Installation of Culverts
2262 | Supply and installation of concrete box culvert components, [1200x300 RCBC] | 9.6 | m |  | 0
Concrete in Culverts and End Structures
2302 | Concrete bases in culverts | 3.1 | m3 |  | 0
2308 | End structures to culverts, reinforced concrete | 0.5 | m3 |  | 0
2313 | Aprons to culverts, reinforced concrete (including cutoff walls) | 0.9 | m3 |  | 0
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 9.35 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 295.2 | m2 |  | 0
Protective Treatments
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 2 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional, If Ordered) | 46 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 1622 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 75 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 650 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 23 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 23 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 577 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 18 | m3 |  | 0
3212P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 577 | m3 |  | 0
3221 | Blinding concrete, [50] mm nominal thickness | 22 | m2 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 121 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 10 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 1528 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 45.8 | m3 |  | 0
3304P | Backfill with select backfill material to (Provisional Quantity, if ordered, allowance to backfill voids in lines of excavation left by rock floaters removed during excavation activities) | 68.8 | m3 |  | 0
Unbound Pavements
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 212.6 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 1343 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 13.9 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 1343 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 31 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
Other
6301P | Remove and dispose of large trees identified for removal - Provisional Quantity - As directed | 6 | each |  | 0
|  |  |  | TOTAL | 0

## A4 - Schedule
SITE 4 - Stabilisation Ch 61565 - 61815
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Supply and Installation of Culverts
2263 | Supply and installation of concrete box culvert components, [1200x600 RCBC] | 18 | m |  | 0
Concrete in Culverts and End Structures
2302 | Concrete bases in culverts | 5.8 | m3 |  | 0
2308 | End structures to culverts, reinforced concrete | 1 | m3 |  | 0
2313 | Aprons to culverts, reinforced concrete (including cutoff walls) | 1.3 | m3 |  | 0
Subsurface Drainage
2515P | Supply and installation of geotextile, Strength Class [E], Filtration Class [II] (Culvert Inlet and Outlet protection), Provisional, As Directed | 92 | m2 |  | 0
Protective Treatments
2644P | Rock protection (Culvert Drop Inlet, D50=200mm), Provisional, As Directed | 22.8 | m3 |  | 0
2645 | Rock protection (Culvert Outelet Protection, D50=300mm) | 6.6 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 1279 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 69 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 786 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 32 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 32 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 513 | m3 |  | 0
3205P | Excavation for diversion channels, all materials (Provisional Quantity, as directed) - Excavation and reshaping of natural channel to achieve positive drainage to culvert inlet. | 62 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 9 | m3 |  | 0
3212P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 154 | m3 |  | 0
3221 | Blinding concrete, [50] mm nominal thickness | 39 | m2 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 147 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 6 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 2120.9 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 63.6 | m3 |  | 0
Unbound Pavements
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 293.8 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 1814 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 18.8 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 1814 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 27 | each |  | 0
Other
6301P | Remove and dispose of large trees identified for removal (Provisional Quantity - as directed) | 15 | each |  | 0
|  |  |  | TOTAL | 0

## A5 - Schedule
SITE 5 - Christmas Creek
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Drainage Removal/Demolition
2101 | Removal or demolition of complete culvert, complete 375 RCP | 1 | Lump Sum |  | 0
2107 | Removal or demolition of concrete slabs (including stone pitching) | 66 | m2 |  | 0
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 332.5 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 164 | m2 |  | 0
Protective Treatments
2631 | Hand placed concrete paving, [175] mm thick, (including cutoff walls) as per project drawings and std drg CMDG-R-094 | 187 | m2 |  | 0
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 159.6 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional, If Ordered) | 25.6 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 3000 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 124 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 1134 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 38 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 38 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 1708 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 33 | m3 |  | 0
3211P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 171 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 213 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 22 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 2532.4 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 76 | m3 |  | 0
3303P | Backfill with select backfill material to (Provisional Quantity, as directed, backfill to demolished RCP trench) | 10 | m3 |  | 0
Unbound Pavements
4102 | Subtype 2.3, Unbound pavement, [floodway] | 37.4 | m3 |  | 0
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 456.7 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 694 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 7.2 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 694 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 25 | each |  | 0
6112 | Road edge guide posts (flexible tubular) | 10 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
Road Deliniation
6301 | Spotting only for longitudinal lines | 28 | m |  | 0
6302 | Pavement marking (all types) | 28 | m |  | 0
|  |  |  | TOTAL | 0

## A6 - Schedule
SITE 6 - Ross Creek
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Drainage Removal/Demolition
2107 | Removal or demolition of concrete slabs (exisiting concrete floodway) | 60 | m2 |  | 0
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 405.6 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 172 | m2 |  | 0
Protective Treatments
2631 | Hand placed concrete paving, [175] mm thick, (including cutoff walls) as per project drawings and std drg CMDG-R-094 | 320 | m2 |  | 0
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 262.4 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional, If Ordered) | 27.6 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 3048 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 154 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 1944 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 52 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 52 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 1180 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 51 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 300 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 34 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 3437 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 103.1 | m3 |  | 0
Unbound Pavements
4102 | Subtype 2.3, Unbound pavement, [floodway] | 64 | m3 |  | 0
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 476.9 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 1555 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 16.1 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 1555 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 54 | each |  | 0
6112 | Road edge guide posts (flexible tubular) | 10 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
6102 | Removal and re-erection of road furniture as detailed in drawings | 1 | Lump Sum |  | 0
Road Deliniation
6301 | Spotting only for longitudinal lines | 40 | m |  | 0
6302 | Pavement marking (all types) | 40 | m |  | 0
Other
6301P | Remove and dispose of large trees identified for removal - Provisional Quanitity - As directed | 9 | each |  | 0
|  |  |  | TOTAL | 0

## A7 - Schedule
SITE 7 - Stabilisation Ch 73650 - 74002
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Supply and Installation of Culverts
2242 | Supply and installation of steel-reinforced concrete pipe culvert components, Class [3], [450] mm diameter, [B1] environment | 14.4 | m |  | 0
Concrete in Culverts and End Structures
2309P | Aprons to culverts, reinforced concrete (Cutoff wall) (Provisional, If Ordered) | 0.2 | m3 |  | 0
2308 | Precast concrete end structures to culverts, [450 RCP winged headwall] | 1 | each |  | 0
2313P | Precast concrete end structures to culverts, (Cutoff wall) (Provisional, If Ordered) | 1 | each |  | 0
Pavement Drainage
2465 | Precast concrete Type 2 Field inlet with precast chamber, [600 x 900, domed inlet grate, including risers to 2.143m deep] (CMDG-D-022 Type 2 without apron or Precast Equivalent) | 1 | each |  | 0
Subsurface Drainage
2515P | Supply and installation of geotextile, Strength Class [E], Filtration Class [II] (Culvert Inlet and Outlet protection), Provisional, As Directed | 76.6 | m2 |  | 0
Protective Treatments
2644P | Rock protection (Culvert Inlet, D50=100mm), Provisional, As Directed | 4.8 | m3 |  | 0
2645 | Rock protection (Culvert Outlet Protection, D50=400mm) | 22.4 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 1684 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 88 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 1946 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 43 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 43 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 608 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 30 | m3 |  | 0
3212P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 304 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 479 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 20 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 2886 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 86.6 | m3 |  | 0
Unbound Pavements
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 419.8 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 2473 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 26.4 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 2473 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 40 | each |  | 0
Other
6301P | Remove and dispose of large trees identified for removal (Provisional Quantity - as directed) | 4 | each |  | 0
|  |  |  | TOTAL | 0

## A8 - Schedule
SITE 8 - Sunny Slopes Creek
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Drainage Removal/Demolition
2107 | Removal or demolition of concrete slabs (including stone pitching) | 83 | m2 |  | 0
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 150 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 804 | m2 |  | 0
Protective Treatments
2658P | Concrete batters (Provisional Quantity, if ordered) | 20 | m3 |  | 0
2631 | Hand placed concrete paving, [175] mm thick, (including cutoff walls) as per project drawings and std drg CMDG-R-094 | 270 | m2 |  | 0
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 110 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional, If Ordered) | 127.7 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 4410 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 298 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 2114 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 9 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 44 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 658 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 40 | m3 |  | 0
3211P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 66 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 737 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 26 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 2921 | m2 |  | 0
3403P | Subgrade treatment Type B, replace with subgrade fill material, minimum 150mm treatment depth, Class A1 Minimum CBR 10 (Provisional Quantity, if ordered) | 40.5 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 53 | m3 |  | 0
Unbound Pavements
4102 | Subtype 2.3, Unbound pavement, [floodway] | 52 | m3 |  | 0
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 409 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 2921 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 31.2 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 2921 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 24 | each |  | 0
6112 | Road edge guide posts (flexible tubular) | 10 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
6101 | Demolition of road furniture as detailed in drawings | 1 | Lump Sum |  | 0
Road Deliniation
6301 | Spotting only for longitudinal lines | 36 | m |  | 0
6302 | Pavement marking (all types) | 36 | m |  | 0
Other
6301P | Remove and dispose of large trees identified for removal - Provisional Quanitity - As directed | 2 | each |  | 0
|  |  |  | TOTAL | 0

## A9 - Schedule
SITE 8 - Unnamed Creek - CH 76680 - 76859
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Drainage Removal/Demolition
2101 | Removal or demolition of complete culvert, complete 450 RCP | 1 | Lump Sum |  | 0
2107 | Removal or demolition of concrete slabs (including stone pitching) | 95 | m2 |  | 0
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 322 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 320 | m2 |  | 0
Protective Treatments
2631 | Hand placed concrete paving, [175] mm thick, (including cutoff walls) as per project drawings and std drg CMDG-R-094 | 172 | m2 |  | 0
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 134.25 | m3 |  | 0
2646 | Rock protection (Floodway Inlet Rock Protection per details on drawings) | 29.2 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional, If Ordered) | 50.8 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 1113 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 76 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 151 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 20 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 20 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 955 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 21 | m3 |  | 0
3211P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 95 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 47 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 14 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 1318 | m2 |  | 0
3403 | Subgrade treatment Type B, replace with subgrade fill material, (Floodway) | 25.8 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 39.5 | m3 |  | 0
3305P | Backfill with select backfill material to (Provisional Quantity, as directed, backfill to demolished RCP trench) | 10 | m3 |  | 0
Unbound Pavements
4102 | Subtype 2.3, Unbound pavement, [floodway] | 34.4 | m3 |  | 0
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 236.7 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 579 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 6 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 579 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 19 | each |  | 0
6112 | Road edge guide posts (flexible tubular) | 6 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
6101 | Demolition of road furniture as detailed in drawings | 1 | Lump Sum |  | 0
Road Deliniation
6301 | Spotting only for longitudinal lines | 24 | m |  | 0
6302 | Pavement marking (all types) | 24 | m |  | 0
Other
6301P | Remove and dispose of large trees identified for removal - Provisional Quanitity - As directed | 3 | each |  | 0
|  |  |  | TOTAL | 0

## A10 - Schedule
SITE 10 - Cracow Creek
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Subsurface Drainage
2515 | Supply & installation of geotextile (Flood Rock Protection) | 260 | m2 |  | 0
Protective Treatments
2631 | Pour in place concrete floodway slab and cut off walls (incluidng all materials) as per drawings | 260 | m2 |  | 0
2642 | Supply and place 420mm depth of D50 300mm rock protection | 100 | m3 |  | 0
General Earthworks
Preparation
3101P | Clearing and grubbing - Provisional Qty | 1000 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 50 | m3 |  | 0
3104P | Ground surface treatment, standard - Provisional Qty | 510 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 20 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 20 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 730 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 21 | m3 |  | 0
3211P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 95 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 1683 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 39.5 | m3 |  | 0
Unbound Pavements
4102P | Council MIx, Unbound pavement, [floodway] - Provisional Quantity as required | 30 | m3 |  | 0
4107 | Council Mix Base, Unbound pavement - Stabilised unsing 2% cement powder to 150mm depth | 106 | m3 |  | 0
4109 | Council Mix Base, Unbound pavement | 232 | m3 |  | 0
Other
6302P | Dewatering - Provisional Item as required due to weather patterns and events | 1 | Lump Sum |  | 0
|  |  |  | TOTAL | 0

## A11 - Schedule
SITE 11 - Downfall Creek
Item Number | Activity | Quantity | Unit of Measure | Rate $ (Ex GST) | Total $ (Ex GST)
Provision for Traffic
1201 | Traffic Management | 1 | Lump Sum |  | 0
Contractor Site Facilities
1101 | Contractor Site Facilities | 1 | Lump Sum |  | 0
Enviromental Management
1316 | Control of Erosion and Sedimentation | 1 | Lump Sum |  | 0
Quality Management
9131 | Supply of As Constructed Survey and Drawings | 1 | Lump Sum |  | 0
Drainage Structures, Retaining Structures & Embankment Slope Protection
Subsurface Drainage
2515 | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Flood Rock Protection) | 375.4 | m2 |  | 0
2515P | Supply & installation of geotextile, strength Class E, Filtration Class (II) (Rock Lined Table Drain - Provisional Quantity, If Ordered | 992.2 | m2 |  | 0
Protective Treatments
2631 | Hand placed concrete paving, [175] mm thick, (including cutoff walls) as per project drawings and std drg CMDG-R-094 | 195 | m2 |  | 0
2647 | Rock protection (Floodway geotextile protection layer, D85 < 75mm | 56.31 | m3 |  | 0
2642 | Rock protection (Floodway Rock Protection per details on drawings) | 176.25 | m3 |  | 0
2643P | Rock protection (Rock lined table drain), (Provisional, If Ordered) | 148.83 | m3 |  | 0
General Earthworks
Preparation
3101 | Clearing and grubbing | 5082 | m2 |  | 0
3103P | Stripping, storage and respreading of topsoil (Provisional Quantity, as directed) | 226 | m3 |  | 0
3104 | Ground surface treatment under embankment, standard | 5482 | m2 |  | 0
3214P | Excavation and disposal of unsuitable material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | 82 | m3 |  | 0
3215P | Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | 82 | m3 |  | 0
Excavation
3201 | Excavation, all materials | 937 | m3 |  | 0
3206P | Excavation for diversion drains, all materials (Provisional Quantity, as directed) | 45 | m3 |  | 0
3211P | Excavation of non-rippable material in Road Excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity) | 937 | m3 |  | 0
Embankment
3301 | Embankment - useable site won cut or local borrow material | 732 | m3 |  | 0
3302 | Levees, catch banks and diversion blocks using earthfill material (Class A1, Class B or local borrow pit material) from all sources | 18 | m3 |  | 0
Existing Subgrade Testing and Treatments
3402P | Subgrade treatment Type A (Provisional Quantity, if ordered) | 5450.7 | m2 |  | 0
3115P | Replacement of Unsuitable Material (Provisional Item, if ordered) | 163.5 | m3 |  | 0
3304P | Backfill with select backfill material to (Provisional Quantity, if ordered, allowance to backfill excavations of unsuitable material) | 245.3 | m3 |  | 0
Unbound Pavements
4107 | Type 4 Base, Subtype [Unsealed Pavement Material as specified on plans], Unbound pavement, | 686.6 | m3 |  | 0
Insitu Stabilisation
4211 | Insitu stabilisation using cement or cementitious blends | 585 | m2 |  | 0
4221 | Supply of stabilising agent [GB cement/Fly Ash, estimated 3% by mass] | 6.1 | Tonne |  | 0
4231 | Water curing [Stabilised Floodway Approaches] | 585 | m2 |  | 0
Road Furniture
6111 | Road edge guide posts (flexible) | 98 | each |  | 0
6112 | Road edge guide posts (flexible tubular) | 14 | each |  | 0
6120 | Supply and erect road signage as detailed in drawings | 1 | Lump Sum |  | 0
6101 | Demolition of road furniture as detailed in drawings | 1 | Lump Sum |  | 0
6103 | Removal and salvage of road furniture, as detailed in drawings | 1 | Lump Sum |  | 0
6102 | Removal and re-erection of road furniture, as detailed in drawings | 1 | Lump Sum |  | 0
Road Deliniation
6301 | Spotting only for longitudinal lines | 30 | m |  | 0
6302 | Pavement marking (all types) | 30 | m |  | 0
Other
6301P | Remove and dispose of large trees identified for removal - Provisional Quanitity - As directed | 11 | each |  | 0
|  |  |  | TOTAL | 0